## Product Backlog
Product Name: |  | Robbie Robot Shop
Team ID: |  | D.A.A.W
Name: |  | William Caballero
Initials: |  | W.C.
Student ID: |  | 1000885642
(Additional names for teams only)
Name: |  | Devony Powell
Initials: |  | D.P.
Student ID: |  | 1001237272
Name: |  | Anena Sims
Initials: |  | A.V.S.
Student ID: |  | 1001138287
Name: |  | Arianne Silvestre
Initials: |  | A.S.
Student ID: |  | 1000921178
Total Features | 21 | Status | Sprint Ends
Sprint 1 Left | 21 | Completed | 2016-10-06
Sprint 2 Left | 21 | Completed | 2016-10-13
Sprint 3 Left | 11 | Completed | 2016-10-20
Sprint 4 Left | 11 | Completed | 2016-10-27
Sprint 5 Left | 11 | Due | 2016-11-03
Sprint 6 Left | 11 | Due | 2016-11-10
Sprint 7 Left | 11 | Due | 2016-11-17
Sprint 8 Left | 11 | Due | 2016-11-22
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Prio | Status | Sprint # | Team Size | As a... | I want to... | So that... | Notes
ALL1 | 1 |  |  | 1 | All | open a GUI main window | I can interact with RRS Manager with my mouse | No menu required here – run program, create a part
| 2 |  |  | 1 | PM | create robot parts | I can define robot models | No menu required here – run program, create a part
PM3 | 3 |  |  | 1 | PM | create robot parts via GUI dialogs | I can define robot models | An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
| 4 |  |  | 1 | PM | define new robot models | RRS can sell them to our Beloved Customers | Menu needed – create parts, then create a robot model
PM5 | 5 |  |  | 1 | PM | define new robot models via GUI dialogs | RRS can sell them to our Beloved Customers | Similar to robot parts (perhaps Create > Robot Model)
| 6 |  |  | 1 | BC | browse a catalog of robots | I can buy one or more robots | Need to list robots models, then list parts in selected model
BC7 | 7 |  |  | 1 | BC | browse a catalog of robots via a GUI report | I can buy one or more robots | A text output is OK initially, but an attractive HTML-like output is desired (perhaps (Report > All Robot Models)
BC8 | 8 |  |  | 1 | BC | see pictures of the robots in the GUI catalog | I can see what I'm buying | Add picture when defining robot model, and show it in the robot model report
| 9 |  |  | 1 | SA | create a robot order for a Customer | I can sell robots and thus do my job well | Select robot model and quantity, show details with total price
PB10 | 10 |  |  | 1 | PB | Create a new Beloved Customer via GUI | I can keep track of who's buying our products | The usual name, address, phone number, and email address (perhaps Create > Customer)
PB11 | 11 |  |  | 1 | PB | Create a new Sales Associate via GUI | I can keep track of my employees' performance | Name and employee number at a minimum (perhaps Create > Sales Associate)
PB12 | 12 |  |  | 1 | SA | Create a robot order for a Customer via GUI | I can sell robots and thus do my job well
| 13 |  |  | 2 | PB | ensure persistence of the RRS data | we don't lose orders or historical data | Write the data to the default filename and reload it next time the program runs
| 14 |  |  | 2 | PB | allow the users to save data explicitly via GUI | we can save data without exiting the program | Write the data to the default filename on command (perhaps File > Save to the default filename)
| 15 |  |  | 2 | PB | allow the users to load data explicitly via GUI | we can manage multiple stores in different files | Read the data from a user-selected file on command (perhaps File > Open)
| 16 |  |  | 2 | PB | allow the users to save data to a specified name via GUI | we can manage multiple stores in different files | Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
| 23 |  |  | 2 | PB / SA | view a list of orders per SA | I can estimate the value of employees / I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
| 24 |  |  | 2 | PB / SA | view a report of orders per SA in the GUI | I can estimate the value of employees / I can justify a raise | A basic text report is fine (perhaps Report > Orders by Sales Associate)
| 17 |  |  | 3 | All | enable basic login by role and customize the GUI | we don't have options that don't apply to our roles | User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
| 18 |  |  | 3 | All | enable copy and paste from text fields | we can save typing | Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
| 21 |  |  | 3 | BC | view my bill | I can pay for my robots | Show a BC invoice. Actual payment is outside the scope of this project
| 22 |  |  | 3 | BC | view my bill (invoice) in the GUI | I can pay for my robots | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
| 25 |  |  | 3 | BC | view my orders | see what I have coming to me | Show list of orders for a BC with total price, then list details of selected order
| 26 |  |  | 3 | BC | view my orders in the GUI | see what I have coming to me | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
| 27 |  |  | 4 | SA | view a sales report | I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
SA28 | 28 |  |  | 4 | SA | view a sales report in the GUI | I can justify a raise | A basic text report is fine (perhaps Report > Orders by Sales Associate)
| 19 |  |  | 4 | PB | view a list of orders | I can manage the company | Show list of every order with total price, then list details of selected order
PB20 | 20 |  |  | 4 | PB | view a report of all orders in the GUI | I can manage the company | A basic text report is fine (perhaps Report > All Orders)
ALL29 | 29 |  |  | 4 | All | Add multi-level undo | Worry less about making mistakes | This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
BC30 | 30 |  |  | 4 | BC | see a pie chart of a model's component costs | I can decide if I want a different model | Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
| 31 |  |  | Bonus | SA | create a bulk (2+) order for Customer via GUI | avoid proliferation of orders and paperwork | Allow more than one robot model (with respective quantity) on a single order
| 32 |  |  | Bonus | PM | hide robot parts via GUI | obsolete parts aren't accidentally used | Mark robot parts as “obsolete” and don't allow adding them to new robot models
| 33 |  |  | Bonus | PM | hide robot models via GUI | obsolete robots aren't ordered | Mark robot models as “obsolete” and don't allow adding them to new orders
| 34 |  |  | Bonus | SA | save a draft order and return to it later via GUI | I can multi-task between indecisive customers | Save an order that hasn't been complete, and allow SA to resume work on it later
| 35 |  |  | Extreme Bonus | BC | browse and order robots over the web | I don't have to talk to the Sales Associates! | (Probably can't address until Homework #6)
| 36 |  |  | Extreme Bonus | PB | avoid any delays in the RRS web software | my SA team is at maximum productivity | This likely means using threads for key processes (Probably can't address until Homework #6)
Formulas:
Sprint Ends = [Sprint Ends, row above]+7

## Sprint 4 Backlog
Sprint # | 4 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2016-10-20
End on | 2016-10-27
Demo on | 2016-10-27
Total Tasks | 11
Day 1 Left | 11
Day 2 Left | 11
Day 3 Left | 11
Day 4 Left | 11
Day 5 Left | 11
Day 6 Left | 11
Day 7 Left | 11
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes

## Sprint 5 Backlog
Sprint # | 5 |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on | 2016-12-27
End on | 2016-11-03
Demo on
Total Tasks | 11
Day 1 Left | 11
Day 2 Left | 11
Day 3 Left | 11
Day 4 Left | 10
Day 5 Left | 10
Day 6 Left | 10
Day 7 Left | 10
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
| ALL 1 | Code | fltk/C++ | A.V.S | Window with menue buttons completed 10/30/16 | Complete
ALL1.1 | ALL1 | Code | fltk/C++ | A.V.S | Create a main window to remain open throughout the prog | Complete | Need to find a way to add menu bar
ALL1.2 | ALL1 | Code | fltk/C++ | A.V.S | Create buttons to select user type (PB, SA, BC, or PM) | Complete
ALL1.3 | ALL1 | Code | fltk/C++ | A.V.S | Create pop-up menus for each of the user types | Complete
ALL1.4 | ALL1 | Code | fltk/C++ | A.V.S | Create dialogue & "ask" boxes to verify user type before executing requested action | Complete
| PM3 | Code | fltk/C++ |  | create robot parts via GUI dialogs | Not Started
PM3.1 | PM3 | Code | fltk/C++ |  | Create a working Makefile to separate all classes in .cpp | Not Started | All classes are in 1 .cpp file. Need to get a working Makefile so classes can be separated into multiple files.
PM3.2 | PM3 | Code | fltk/C++ |  | Display a dialogue box giving user propmpts | Not Started
PM3.3 | PM3 | Code | fltk/C++ |  | Take user input via GUI dialogs | Not Started
PM3.4 | PM3 | Code | fltk/C++ |  | Save the robot parts via GUI dialogs & files | Not Started